## Sheet1
Feature | Description | Deliverable | Time Estimate (hours) | Priority
Design
Core Gameplay Design | Rule Book | Complete Rule Book | 5 | 1
Player Interaction
Player can place units | User can drag units from HUD to screen | Ability for Player to place units during planning phase | 6 | 7
Player can place towers | User can drag units from HUD to screen | Ability for Player to place towers during planning phase | 2 | 7
UI interaction | In-Game UI interaction and HUD | Functioning UI and HUD | 8 | 5
Menu navigation | Main Menu and navigation | Functioning Menu | 7 | 5
Art / Visual Design
Splash Screen Design | Opening logo to our game | Splash Screen Implemented | 4 | 12
UI Design | In-Game HUD which user will interact with | Final UI mock-up | 6 | 4
Map Design | Single map needs to be designed | Finalize concept for level including visual design + gameflow | 20 | 6
Character Design | All minions and towers need to be designed | Finalize concept art for all minions and towers, as well as mothership | 20 | 4
Systems
Unit movement | Minions are able to travel from spawn to enemy mothership | Test-able build with unit movement | 7 | 7
Minion Combat Systems | Minions can attack enemy minions | Test-able build with finalized minion combat system | 14 | 2
Tower Combat Systems | Towers can attack enemy minions | Test-able build with finalized tower combat system | 10 | 2
Win Condition Logic | Game is won when enemy mothership is destroyed | Final win condition implemented into prototype | 3 | 3
Singleplayer enemy AI | User can play against an AI controlled player | Functioning Single-Player match | 30 | 11
Social Integration
Pulling profile information | Understanding and implementing facebook API | Concrete understanding and ability to pull user information using facebook API | 10 | 8
Stat Tracking | User information would be used for stat-tracking | Working leaderboard using stat-tracking | 5 | 11
Tournament Mode (Modes) |  | Functioning Tournament Mode | 9 | 10
Audio Design
Background Music | Ambient music for both planning and battle phase | Background music created and implemented | 24 | 9
Battle Sound Effects | Tower and minion sound effects | Sound Effects created and implemented | 8 | 8
UI Sound Effects | Menu and HUD sound effects | Sound Effects created and implemented | 5 | 8
Microtransactions
Addon Minions |  | AddOn Minions are purchasable and function in game | 10 | 8
Addon Towers |  | AddOn Towers are purchasable and function in game | 10 | 8
Aesthetic Customization |  | Aesthetic Customization are purchasable and function in game | 10 | 8
Storefront |  | Storefront | 15 | 8